## Sheet1
| ID | duration | SAND | field | Y | oil_before | activity_type | Start | pad | cost | Permit | State | oil_after | rig_type | Pending | X | LATITUDE | earliest_start | STATUS | well | Rig | OFI | Pinned | job_description | fluid_before | fluid_after | Notes | LONGITUDE | predecessors | duration_days | End | month_num
0 | YCAC-021_C1.1_2025-4-8 | 144 | TI | YUCA | 9948775 | 235 | C1.1 | 2025-03-27 05:00 | YUCA 07 | 700000 | FALSE | 0 | 235 | rig |  | 301960 | -0.46322 |  | PRODUCING | YCAC-021 | SINOPEC - 932 | 4.612 | FALSE | Pulling Simple (Reemplazo BES) | 1995 | 1995 |  | -76.7795 |  | 8 | 2025-04-04 05:00 | 4
3 | ACAC-166_C1.5_2025-4-7 | 480 | TI | AUCA |  | 20 | C1.5 | 2025-04-15 05:00 | AUCA 27 | 1000000 | FALSE | 0 | 155 | rig |  |  | -0.73139 |  | PRODUCING | ACAC-166 | TUSCANY - 111 | 4.503 | FALSE | Pulling Pesca | 105 | 900 |  | -76.8789 |  | 22 | 2025-05-07 05:00 | 5
4 | CHSA-011_C1.1_2025-4-7 | 168.25 | UI | CHONTA SUR |  | 175 | C1.1 | 2025-04-04 05:00 | CHONTA SUR 01 | 700000 | FALSE | 0 | 175 | rig |  |  | -0.92301 |  | PRODUCING | CHSA-011 | TUSCANY - 111 | 4.792 | FALSE | Pulling Simple (Reemplazo BES) | 185 | 185 |  | -76.9293 |  | 9.0104 | 2025-04-13 05:15 | 4
6 | ACAE-082_C1.12_2025-7-1 | 144 | BT | AUCA | 9922364.71 | 285 | C1.12 | 2025-06-15 05:00 | AUCA 35 | 850000 | FALSE | 0 | 120 | rig |  | 291168.26 | -0.70201 |  | PRODUCING | ACAE-082 | SINOPEC - 932 | 3.517 | FALSE | Pulling Simple + Adquisición de equipos Nuevos de Amplio Rango | 2055 | 1390 |  | -76.8765 |  | 8 | 2025-06-23 05:00 | 6
7 | CNOI-041_C1.7_2025-5-19 | 288 | UI | CONONACO | 9885566.69 | 275 | C1.7 | 2025-05-30 05:00 | CONONACO 34 | 850000 | FALSE | 0 | 237 | rig |  | 283411.32 | -1.0347 | 2025-05-29T05:00:00 | PRODUCING | CNOI-041 | SINOPEC - 932 | 5.542 | FALSE | Pulling Simple + Estimulacion + Evaluacion | 280 | 300 |  | -76.9464 |  | 14 | 2025-06-13 05:00 | 6
8 | CLBC-055_C1.7_2025-4-13 | 288 | UI | CULEBRA | 9948690.35 | 235 | C1.7 | 2025-06-18 05:00 | CULEBRA 21 | 307243 | FALSE | 2 | 150 | rig |  | 287830.843 | -0.46396 |  | DRILLING | CLBC-055 | SINOPEC - 932 | 0 | FALSE | Pulling Simple + Estimulacion + Evaluacion | 400 | 300 |  | -76.9064 |  | 14 | 2025-07-02 05:00 | 7
9 | CLBB-034_C1.1_2025-7-1 | 168 | UI | CULEBRA |  | 150 | C1.1 | 2025-06-07 05:00 | CULEBRA 08 | 800000 | FALSE |  | 150 | rig |  |  | -0.47912 | 2025-06-07T05:00:00 | PRODUCING | CLBB-034 | ORIENDRILL 903 | 3.942 | FALSE | Pulling Simple (Reemplazo BES) | 190 | 150 |  | -76.9087 |  | 9 | 2025-06-16 05:00 | 6
10 | CLB-005_C1.1_2025-7-1 | 144 | UI | CULEBRA |  | 180 | C1.1 | 2025-06-24 05:00 | CULEBRA 05 | 850000 | FALSE | 0 | 150 | rig |  |  | -0.48435 |  | PRODUCING | CLB-005 | ORIENDRILL 903 | 3.763 | FALSE | Pulling Simple (Reemplazo BES) | 780 | 300 |  | -76.9004 |  | 8 | 2025-07-02 05:00 | 7
12 | ACAH-192_C1.1_2025-7-1 | 144 | TI | AUCA |  | 305 | C1.1 | 2025-07-01 05:00 | AUCA 53 | 850000 | FALSE | 0 | 185 | rig |  |  | -0.68027 |  | PRODUCING | ACAH-192 | ORIENDRILL 903 | 3.157 | FALSE | Pulling Simple (Reemplazo BES) | 345 | 300 |  | -76.8763 |  | 8 | 2025-07-09 05:00 | 7
13 | YLBD-044H_C1.12_2025-7-1 | 192 | UI | YULEBRA |  | 1850 | C1.12 | 2025-06-15 05:00 | YULEBRA - 03 | 850000 | FALSE | 0 | 1850 | rig |  |  | -0.47702 |  | PRODUCING | YLBD-044H | ORIENDRILL 903 | 0 | FALSE | Pulling Simple + Adquisición de equipos Nuevos de Amplio Rango | 2800 | 2800 |  | -76.8701 |  | 10 | 2025-06-25 05:00 | 6
14 | TTSA-002_C1.7_2025-4-20 | 144 | UI | TORTUGA SUR | 9905214.255 | 92 | C1.7 | 2025-07-27 05:00 | TORTUGA SUR | 1000000 | FALSE | 0 | 120 | rig |  | 283071.309 | -0.85706 |  | PRODUCING | TTSA-002 | TUSCANY - 111 | 2.502 | FALSE | Pulling Simple + Estimulacion + Evaluacion | 94 | 125 |  | -76.9493 |  | 8 | 2025-08-04 05:00 | 8
15 | YLBD-023H_C1.3_2025-7-14 | 240 | UI | YULEBRA |  | 900 | C1.3 | 2025-07-07 05:00 | YULEBRA 03 | 1000000 | FALSE | 0 | 875 | rig |  |  | -0.47681 |  | PRODUCING | YLBD-023H | ORIENDRILL 903 | 4.953 | FALSE | Pulling Simple + Recanoneo TCP + Evaluacion | 2185 | 2500 |  | -76.87 |  | 12 | 2025-07-19 05:00 | 7
16 | YLBA-030_C1.2_2025-7-2 | 336 | UI | YULEBRA | 9946549.775 | 0 | C1.2 | 2025-07-23 05:00 | YULEBRA 02 | 1000000 | FALSE | 0 | 0 | rig |  | 291281.417 | -0.48332 |  | DRILLING | YLBA-030 | SINOPEC - 932 | 2.977 | FALSE | Pulling Simple + Recanoneo WL | 0 | 2500 |  | -76.8754 |  | 16 | 2025-08-08 05:00 | 8
17 | CLBC-047H_C1.3_2025-8-3 | 264 | UI | CULEBRA | 9948519.51 | 888 | C1.3 | 2025-08-04 05:00 | CULEBRA 21 | 296779 | FALSE | 0 | 1050 | rig |  | 288785.1 | -0.4655 | 2025-08-04T05:00:00 | EWO | CLBC-047H | TUSCANY - 111 | 3.1 | FALSE | Pulling Simple + Recanoneo TCP + Evaluacion | 1708 | 2100 |  | -76.8978 | TTSA-002_C1.7_2025-4-20 | 13 | 2025-08-17 05:00 | 8
19 | YLBD-045HST1_C1.1_2025-7-14 | 168 | UI | YULEBRA | 9947249.642 | 490 | C1.1 | 2025-07-15 05:00 | YULEBRA - 03 | 800000 | FALSE |  | 790 | rig |  | 291874.014 |  |  | DRL_PLAN | YLBD-045HST1 | SINOPEC - 932 | 0 | FALSE | Pulling Simple (Reemplazo BES) | 930 | 1800 |  |  |  | 9 | 2025-07-24 05:00 | 7
20 | YCAF-030_C1.1_2025-7-2 | 192 | UI | YUCA |  | 220 | C1.1 | 2025-07-18 05:00 | YUCA 29 | 85000 | FALSE | 0 | 190 | rig |  |  | -0.45635 |  | PRODUCING | YCAF-030 | ORIENDRILL 903 | 3.487 | FALSE | Pulling Simple (Reemplazo BES) | 1705 | 1745 |  | -76.7975 |  | 10 | 2025-07-28 05:00 | 7
24 | ACAI-106R1_C1.12_2025-5-12 | 144 | UI | AUCA |  | 190 | C1.12 | 2025-05-23 05:00 | AUCA 06 | 800000 | FALSE | 0 | 475 | rig |  |  | -0.6361 |  | DRILLING | ACAI-106R1 | SINOPEC - 932 | 3.687 | FALSE | Pulling Simple + Adquisición de equipos Nuevos de Amplio Rango | 590 | 2500 |  | -76.8777 |  | 8 | 2025-05-31 05:00 | 5
27 | ACSD-015_C1.2_2025-4-7 | 312 | UI | AUCA SUR | 9913770.21 | 175 | C1.2 | 2025-04-20 05:00 | AUCA SUR 02 | 800000 | FALSE | 0 | 130 | rig |  | 290361.81 | -0.77972 |  | PRODUCING | ACSD-015 | SINOPEC - 932 | 4.385 | FALSE | Pulling Simple + Recanoneo WL | 1175 | 695 |  | -76.8838 |  | 15 | 2025-05-05 05:00 | 5
29 | ACAL-139_C1.2_2025-7-1 | 216 | TI | AUCA | 9934927.89 | 125 | C1.2 | 2025-08-18 05:00 | AUCA 137 | 920000 | FALSE | 0 | 125 | rig |  | 287125.97 | -0.5884 |  | PRODUCING | ACAL-139 | TUSCANY - 111 | 2.675 | FALSE | Pulling Simple + Recanoneo WL | 210 | 210 |  | -76.9128 |  | 11 | 2025-08-29 05:00 | 8
30 | ACAC-112_C1.1_2025-8-3 | 168 | HI | AUCA |  | 0 | C1.1 | 2025-09-18 05:00 | AUCA 27 | 190198 | FALSE | 3 | 1 | rig |  |  | -0.73168 |  | PRODUCING | ACAC-112 | ORIENDRILL 903 | 3.962 | FALSE | Pulling Simple (Reemplazo BES) | 3200 | 3200 |  | -76.8789 | YLBA-030_C1.2_2025-7-2 | 9 | 2025-09-25 05:00 | 9
34 | ACAK-180_C1.1_2025-7-14 | 144 | HI | AUCA |  | 0 | C1.1 | 2025-10-03 05:00 | AUCA 123 | 700000 | FALSE | 0 | 1 | rig |  |  | -0.56833 |  | PRODUCING | ACAK-180 | Braserv-101 | 2.502 | FALSE | Pulling Simple (Reemplazo BES) | 3200 | 3200 |  | -76.9012 |  | 8 | 2025-10-11 05:00 | 10
35 | CNOE-030_C1.2_2025-7-1 | 168 | TI | CONONACO | 9890695.731 | 89 | C1.2 | 2025-09-05 05:00 | CONONACO 14 | 800000 | FALSE | 0 | 95 | rig |  | 285049.793 | -0.98834 |  | PRODUCING | CNOE-030 | ORIENDRILL 903 | 2.893 | FALSE | Pulling Simple + Recanoneo WL | 95 | 97 |  | -76.9316 |  | 9 | 2025-09-14 05:00 | 9
36 | ACAI-085_C1.5_2025-5-12 | 480 | HI | AUCA |  | 0 | C1.5 | 2025-11-17 05:00 | AUCA 06 | 346705.88 | FALSE | 0 | 1 | rig |  |  | -0.63617 |  | PRODUCING | ACAI-085 | ORIENDRILL 903 | 3.4 | FALSE | Pulling Pesca | 8000 | 8000 |  | -76.8777 |  | 22 | 2025-12-09 05:00 | 12
42 | ACA-055I_C1.14_2025-8-25 | 168 | TY | AUCA | 9928582.9 | 0 | C1.14 | 2025-10-30 05:00 | ACA-055 | 1 | FALSE | 0 | 1 | rig |  | 290459.4 | -0.64578 |  | INYECTING | ACA-055I | Braserv-101 | 4.417 | FALSE | Pulling Simple Pozo Inyector o Reinyector Sencillo | 8000 | 8000 |  | -76.8829 |  | 9 | 2025-11-08 05:00 | 11
43 | ACAL-139_C1.3_2025-8-18 | 408 | TS | AUCA | 9919620.26 | 1 | C1.3 | 2025-08-17 05:00 | AUCA 126 | 900000 | FALSE | 0 | 1025 | rig |  | 294070.64 | -0.72684 | 2025-06-14T05:00:00 | DRILLING | ACAL-139 | TUSCANY - 111 | 3.723 | FALSE | Pulling Simple + Recanoneo TCP + Evaluacion | 1 | 1025 |  | -76.8505 |  | 19 | 2025-09-03 05:00 | 9
44 | ACAK-121_C1.1_2025-8-25 | 168 | HS | AUCA | 9937145.663 | 130 | C1.1 | 2025-10-10 05:00 | AUCA 123 | 1000000 | FALSE | 0 | 215 | rig |  | 288444.846 | -0.56835 |  | INACTIVE | ACAK-121 | Braserv-101 | 2.918 | FALSE | Pulling Simple (Reemplazo BES) | 150 | 250 |  | -76.9009 |  | 9 | 2025-10-19 05:00 | 10
45 | YCA-013R1_C1.2_2025-8-25 | 168 | HS | YUCA | 9947744.7 | 110 | C1.2 | 2025-11-07 05:00 | YCA-013 | 1000000 | FALSE | 0 | 150 | rig |  | 302802.5 | -0.47254 |  | PRODUCING | YCA-013R1 | Braserv-101 | 4.508 | FALSE | Pulling Simple + Recanoneo WL | 340 | 500 |  | -76.7719 |  | 9 | 2025-11-16 05:00 | 11
47 | YCAC-048_C1.2_2025-8-25 | 168 | UI | YUCA | 9948774.48 | 0 | C1.2 | 2025-11-15 05:00 | YUCA 07 | 1000000 | FALSE | 0 | 150 | rig |  | 301975.85 | -0.46323 |  | DRILLING | YCAC-048 | Braserv-101 | 2.972 | FALSE | Pulling Simple + Recanoneo WL | 0 | 1000 |  | -76.7794 |  | 9 | 2025-11-24 05:00 | 11
48 | ACAK-181_C1.7_2025-7-14 | 264 | TI | AUCA | 9937147.578 | 0 | C1.7 | 2025-10-18 05:00 | AUCA 123 | 1000000 | FALSE | 0 | 126 | rig |  | 288414.895 | -0.56833 |  | PRODUCING | ACAK-181 | Braserv-101 | 2.778 | FALSE | Pulling Simple + Estimulacion + Evaluacion | 0 | 1255 |  | -76.9012 |  | 13 | 2025-10-31 05:00 | 10
50 | CNO-009_C1.1_2025-8-3 | 168 | UI | CONONACO | 9887447.868 | 135 | C1.1 | 2025-08-28 05:00 | CONONACO 09 | 190198 | FALSE | 0 | 135 | rig |  | 284140.804 | -1.0177 |  | PRODUCING | CNO-009 | ORIENDRILL 903 | 5.055 | FALSE | Pulling Simple (Reemplazo BES) | 172 | 172 |  | -76.9398 |  | 9 | 2025-09-06 05:00 | 9
56 | ACAP-100_C1.5_2025-9-3 | 462 | UI | AUCA | 9933602.36 | 291 | C1.5 | 2025-11-21 05:00 | AUCA 56 | 1999968 | FALSE |  | 291 | rig |  | 289643.75 | -0.60039 |  | PRODUCING | ACAP-100 | SINOPEC - 932 | 3.602 | FALSE | Pulling Pesca | 320 | 320 |  | -76.8902 |  | 21.25 | 2025-12-12 11:00 | 12
57 | ACAG-076_C1.1_2025-8-25 | 168 | UI | AUCA | 9933073.67 | 20 | C1.1 | 2025-09-16 05:00 | AUCA 51 | 850000 | FALSE | 0 | 85 | rig |  | 291240.59 | -0.60518 |  | PRODUCING | ACAG-076 | SINOPEC - 932 | 2.452 | FALSE | Pulling Simple (Reemplazo BES) | 100 | 1045 |  | -76.8758 |  | 9 | 2025-09-25 05:00 | 9
58 | ACAR-269H_C1.7_2025-4-7 | 288 | TS | AUCA | 9919600.992 | 0 | C1.3 | 2025-09-02 05:00 | AUCA 126 | 1325184 | FALSE | 2 | 460 | rig |  | 294090.951 |  |  | SUSPENDED | ACAR-269H | SINOPEC - 932 | 0 | FALSE | Pulling Simple + Recanoneo TCP + Evaluacion | 0 | 460 |  |  |  | 14 | 2025-09-16 05:00 | 9