## Sheet1
month_num | MONTH | TOTAL_ACTIVITIES | FORECAST_COST | C1.1_COUNT | C1.1_COST | C1.2_COUNT | C1.2_COST | C1.3_COUNT | C1.3_COST | C1.4_COUNT | C1.4_COST | C1.5_COUNT | C1.5_COST | C1.6_COUNT | C1.6_COST | C1.7_COUNT | C1.7_COST | C1.8_COUNT | C1.8_COST | C1.9_COUNT | C1.9_COST | C1.10_COUNT | C1.10_COST | C1.11_COUNT | C1.11_COST | C1.12_COUNT | C1.12_COST | C1.13_COUNT | C1.13_COST | C1.14_COUNT | C1.14_COST | C1.15_COUNT | C1.15_COST | C1.16_COUNT | C1.16_COST | ACTUAL_COST | BUDGET | CUMULATIVE_FORECAST
1 | January | 6 | 63944 | 2 | 13276 | 2 | 13276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 37392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 44155.32 | 44155.32 | 44155.32
2 | February | 5 | 45248 | 1 | 6638 | 2 | 13276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 18696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 51275.6786 | 51275.6786 | 95430.9986
3 | March | 7 | 58971 | 3 | 19914 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 19143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 19914 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55536.23 | 55536.23 | 150967.2286
4 | April | 3 | 19914 | 2 | 13276 | 1 | 6638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 19914 | 170881.2286
5 | May | 2 | 25781 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 19143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 25781 | 196662.2286
6 | June | 11 | 127512 | 4 | 26552 | 1 | 6638 | 1 | 6638 | 0 | 0 | 1 | 19143 | 0 | 0 | 1 | 18696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 13276 | 0 | 0 | 1 | 36569 | 0 | 0 | 0 | 0 |  | 127512 | 324174.2286
7 | July | 10 | 90943 | 4 | 26552 | 1 | 6638 | 1 | 6638 | 0 | 0 | 1 | 19143 | 0 | 0 | 1 | 18696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 13276 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 90943 | 415117.2286
8 | August | 8 | 65162 | 4 | 26552 | 1 | 6638 | 1 | 6638 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 18696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 65162 | 480279.2286
9 | September | 6 | 51886 | 3 | 19914 | 1 | 6638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 18696 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 51886 | 532165.2286
10 | October | 5 | 33190 | 3 | 19914 | 1 | 6638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 33190 | 565355.2286
11 | November | 5 | 33190 | 3 | 19914 | 1 | 6638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 33190 | 598545.2286
12 | December | 5 | 33190 | 3 | 19914 | 1 | 6638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 6638 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 33190 | 631735.2286